## Preliminaries
SECTION 1
PRELIMINARIES
SPECIAL NOTES
1 | The Contractor is required to check the numbers of the pages and should any be found to be missing or
in duplicate or the figures or writing indistinct, they must inform the Quantity Surveyors at once and have
the same rectified. Should the Contractor be in doubt about the precise meaning of any item, word or
figure, for any reason whatsoever, or observe any apparent omission of words or figures they must inform
the Quantity Surveyor in order that the correct meaning may be decided upon before the date for the
submission of the Tender.
2 | No liability whatever will be admitted nor claim allowed in respect of errors in the Contractor's Tender
due to mistakes in the Bills of Quantities which should have been rectified in the manner described
above.
3 | Any doubt or obscurity as to the meaning or intention of any part of the tender documents, or any
question arising, shall be taken up in writing, before submission of the tender so that the same can
be clarified.
4 | The Contractor shall not alter or otherwise qualify the text of these Bills of Quantities. Any alteration
or qualification made without authority will be ignored and the text of the Bills of Quantities as
printed will be adhered to.
5 | The Contractor shall be deemed to have made allowance in their prices generally to cover items of
Preliminaries or additions to Prime Cost Sums or other items, if these have not been priced against the
respective items.
6 | All items of measured work shall be priced in detail and tenders containing lump sums to cover trades or
groups of work must be broken down to show prices for each item before they will be accepted.
Lump sums to cover items of Preliminaries shall likewise be broken down if so required.
7 | In no case will any expenses incurred by Contractors in preparation of this Tender be reimbursed.
8 | The copyright of these Bills of Quantities is vested in the Quantity Surveyors and no part thereof may
be reproduced without their express permission given in writing.
9 | The Contractor is solely responsible for the accurate ordering of materials in accordance with the
Drawings and Architect's instructions and no claims for any loss or expense will be entertained for
orders for materials based upon the Bills of Quantities.
10 | The Bills of Quantities must be priced in US Dollar currency, i.e. US Dollars and Cents.
11 | The tender documents must be priced in ink.
INDEX
| SECTION NO. 1 |  |  | PRELIMINARIES AND GENERAL DESCRIPTIONS
| SECTION NO. 2 |  |  | ELEVATED WATER TANK
| SECTION NO. 3 |  |  | GENERATOR SHED
| SECTION NO. 4 |  |  | BOREHOLE
| SECTION NO. 5 |  |  | PIPELINE
| SECTION NO. 6 |  |  | CARETAKERS ROOM
| SECTION NO. 7 |  |  | WATER KIOSK
| SECTION NO. 8 |  |  | FENCE
| SECTION NO. 9 |  |  | GRAND SUMMARY
ITEM | DESCRIPTION | [7 empty] | AMOUNT
SECTION NO. 1
PRELIMINARIES AND GENERAL DESCRIPTIONS
PRELIMINARY PARTICULARS
A | PARTIES
| The "Employer" is |  |  |  | INTERNATIONAL ORGANIZATION FOR MIGRATION
For the purpose of the works which are under the control of the consultants above, the
respective consultants shall be deemed to be invested with the duties and be representatives
of the Architect.
B | SITE
The site is located on GALKAYO DISTRICT
The site of the works shall be used solely for the purpose of executing and completing the
Contract to the satisfaction of the Architect.
The Contractor shall obtain the Architect's approval for the siting of all temporary storage
areas for materials.
The Contractors shall visit the site to acquaint themselves with its nature and position, the
nature of the ground, sub- strata and other local conditions, position of power and water
supplies, access roads or any other limitations, and no claims for extras will be considered
on account of lack of knowledge in this respect.
The Contractor's attention is drawn to the fact that they shall confine themselves to the area
necessary for executing the works as instructed by the Architect.
The contractor must obtain the Architect's approval and directions regarding the use of any
materials found on the Site. Any such material utilized in the execution of the Contract shall be
measured and value assessed by the Quantity Surveyor and the amount credited to the
Employer.
[5 empty] | Carried To Collection |  |  | US$
GENERAL MATTERS
A | SUFFICIENCY OF TENDER
The Contractor shall be deemed to have satisfied themselves before tendering as to the
correctness and sufficiency of their Tender for the Works and of the rates and prices stated
in the priced Bills of Quantities, which rates and prices shall cover all their obligations under the
Contract and all matters and things necessary for the proper completion and maintenance of
the Works.
B | STAMP CHARGES
The Contractor shall allow for the payment of all Stamp Charges in connection with the Surety
Bond and Contract Agreement.
C | DEFINITIONS AND ABBREVIATIONS
Terms used in these Bills of Quantities shall be interpreted as follows:
| "Approved" |  | shall mean approved by the Architect.
| "as directed" |  | shall mean as directed by the Architect or any other consultant in the contract.
| "BS" |  | Shall mean the current British Standard Specification published by the British
Standards Institution, 2 Park Street, London W.1, England.
| "CM" |  | shall mean Cubic Meters.
| "SM" |  | shall mean Square Meters.
| "LM" |  | shall mean Linear Meters.
| "mm" |  | shall mean Millimeters.
| "Kg" |  | shall mean Kilograms.
| "No." |  | shall mean Number.
| "m.s" |  | shall mean Measured separately.
| "Ditto " |  | shall mean as described before or as above described.
D | PROGRESS SCHEDULE
The Contractor shall, upon receiving instructions to proceed with the work, draw up a Time
and Progress Schedule setting out the order in which the Works are to be carried out with the
appropriate dates thereof. This Time and Progress Schedule is to be agreed with the Architect
and no deviation from the order set out in this Schedule will be permitted without the written
consent of the Architect. The Main Contractor will be responsible for arranging the above
programme with all Sub-Contractors including the Nominated Sub-Contractors and Nominated
Suppliers.
E | FIGURED DIMENSIONS
Figured dimensions are to be followed in preference to dimensions scaled from the Drawings;
but whenever possible dimensions are to be taken on the Site or from the Buildings. Before
any work is commenced by Sub-Contractors or Specialist Firms, dimensions must be checked
on the Site and/or buildings and agreed with the Contractor, irrespective of the comparable
dimensions shown on the Drawings. The Contractor shall be responsible for the accuracy of
such dimensions.
[5 empty] | Carried To Collection |  |  | US$
A | PROVISIONAL WORK
All "provisional" and other work liable to adjustment under this Contract shall be left uncovered
for a reasonable time to allow all measurements needed for such adjustment to be taken by
the Quantity Surveyor. Immediately the work is ready for measurement, the Contractor shall
give notice to the Quantity Surveyor.
If the Contractor makes default in these respects he shall, if the Architect so directs, uncover
the work at his own expense to enable the measurements to be taken.
B | EXISTING SERVICES
Prior to commencement of any work the Contractor is to ascertain from the relevant
Authorities the exact position, depth and level of all existing electric cables, water pipes or
other services in the area and they shall make whatever provisions may be required by the
Authorities concerned for the support and protection of such services. Any damage or
disturbance caused to any services shall be reported immediately to the Architect and the
relevant Authority and shall be made good to their satisfaction at the Contractor's expense.
C | TRANSPORT TO AND FROM THE SITE
The Contractor shall include in their prices for the transport of materials, workmen, etc., to and
from the Site of the proposed Works, at such hours and by such routes as are permitted by
the Authorities.
D | OVERTIME
The Contractor shall allow in their tender for any extra costs for overtime working they
consider will be necessary in order to complete the works by the contract Date of Completion.
If during the course of the Contract overtime is worked for a specific purpose in accordance
with a written instruction issued by the Architect, the Contractor will be reimbursed in respect
of such overtime to the extent only of the additional net cost of unproductive time payable
over and above the basic hourly rates as laid down by the Regulations of Wages and
Conditions of Employment Act, Building and Construction Industry Wages council and
excluding any bonuses, profits and overheads.
E | PUBLIC AND PRIVATE ROADS, PAVEMENTS, ETC.
The Contractor will be required to make good, at their own expense, any damage they may
cause to the present road surfaces and pavements within or beyond the boundary of the Site,
during the period of the Works. In particular, all existing trees, shrubs, plants, etc., which may
be destroyed or damaged during the progress of the Works are to be made good by the
Contractor to the approval of the Architect.
F | POLICE REGULATIONS
The Contractor is to allow for complying with all instructions and regulations of the
Police Authorities.
[6 empty] | Carried To Collection |  | US$
A | CONTRACTORS' SUPERINTENDENCE
The Contractor shall constantly keep on the Works a literate English-speaking Agent or
Representative, competent and experienced in the kind of work involved, who shall give
his whole time to the superintendence of the Works. Such Agent or Representative shall
receive on behalf of the Contractor, directions and instructions from the Architect and such
directions and instructions shall be deemed given to the Contractor in accordance with the
Conditions of Contract. The Agent shall not be replaced without the specific approval of the
Architect.
It is to be a specific condition of this Contract that the successful Tenderer shall provide
on site throughout the period from the completion of the substructure to the Date for
Practical Completion a suitably qualified, experienced and competent person to ensure
that the works are carried out to the standard required by the specification and detailed
on the Drawings; and shall ensure that upon any termination of employment a suitable
replacement is found.
Before the Tenderer's offer is accepted the Architect will personally interview the Contractor's
proposed Representative. A curriculum vitae of past experience and qualifications must be
provided for the Architect's scrutiny.
The Architect's decision will be final regarding the suitability of the proposed Representative.
B | WATER
All water shall be fresh, clean and pure, free from earthy vegetable or organic matter, acid or
alkaline substance in solution or suspension.
The Contractor shall provide at their own risk and cost all water for use in connection with the
Works (including the work of Sub-Contractors). The Contractor shall provide at their own
expense all temporary distribution pipes, storage tanks, meters, etc., and they shall clear
away same upon completion of the Works.
C | LIGHTING AND POWER
The Contractor shall provide at their own risk and cost all artificial lighting and power for use
on the Works, including all Sub-Contractors' and Specialists' requirements and including all
temporary connections, wiring, fittings, etc., and clearing away on completion. The Contractor
shall pay all fees and obtain all permits in connection therewith.
D | SAFETY
In particular there shall be proper provision of planked footways and guard-rails to scaffolding,
etc.; protection against falling materials and tools and the Site shall be kept tidy and clear of
dangerous rubbish.
The Architect shall be empowered to suspend work on the Site should he consider these
conditions are not being observed, and no claim arising from such a suspension will be allowed.
[5 empty] | Carried To Collection |  |  | US$
A | PROTECTIVE CLOTHING
The Contractor shall provide all protective or any other special clothing or equipment for their
employees that may be necessary.
These shall include, inter-alia, safety helmets, gloves, goggles, earmuffs, gumboots, steel
toed boots, overalls, etc according to the type of work. The Contractor shall ensure
that all safety and protective gear are worn by all staff on site at all times
MATERIALS AND WORKMANSHIP
B | GENERALLY
All materials shall be new unless otherwise directed or permitted by the Architect and in all
cases where the quality of goods or materials is not described or otherwise specified, is to be
the best quality obtainable in the ordinary meaning of the word "best" and not merely a trade
signification of that word.
All materials and workmanship shall, unless otherwise specified or described, conform to the
appropriate Kenya Bureau of Standards or British Standards Institution Specification current
at the date of tender.
The Contractor shall order all materials to be obtained from overseas immediately after the
Contract is signed and shall also order materials to be obtained from local sources as early as
necessary to ensure that such materials are on Site when required for use in the Works.
The Contractor shall be responsible for and shall replace or make good at their own expense
any materials lost or damaged.
The Works throughout shall be executed by skilled workmen well versed in their respective
trades.
C | REJECTED WORKMANSHIP OR MATERIALS
Any workmanship or materials not complying with the specific requirements or approved
samples or which have been damaged, contaminated or have deteriorated, must immediately
be removed from the Site and replaced at the Contractor's expense, as required.
D | PROPRIETARY MATERIALS
Where proprietary materials are specified herein-after the Contractor may propose the use of
materials of other manufacture but equal quality for approval by the Architect.
All materials and goods, where specified to be obtained from a particular manufacturer or
supplier are to be used or fixed strictly in accordance with their instructions.
E | SAMPLES
The Contractor shall furnish at the earliest possible opportunity before work commences and
at his own cost, any samples of materials or workman-ship that may be called for by the
Architect for his approval or rejection, and any further samples in the case of rejection until
such samples are approved by the Architect and such samples, when approved, shall be the
minimum standard for the work to which they apply.
[5 empty] | Carried To Collection |  |  | US$
A | CONCRETE TESTS
Concrete test cubes I.e. per set of three as later described, including testing fees, labour
and materials, making moulds, transport and handling etc.. and ensuing copies of tests
are promptly dispatched to the Architect's and Quantity Surveyor's offices.
Successful tests only (Provisional)
TEMPORARY WORKS
B | SPACE AND SERVICES FOR THE ARCHITECT
The Contractor shall provide where directed within the site, site offices and clean toilet facilities
for the sole use of the Architect and their representatives to the satisfaction of the Local
Authorities. The offices shall be provided with adequate furniture and the contractor shall
provide the services of a sweeper, pay all charges and keep the facilities in a clean and
sanitary condition during the whole period of the Works. In particular, the Contractor is to
note that the station will continue with operations during the period of the works and a
separate office and store shall be provided for full time use by the station dealer. Equally,
separate sanitary amenities shall be provided for the station staff to the satisfaction of the
Architect and local authorities.
C | TELEPHONE
The Contractor shall provide a telephone connection to the town exchange for the period of
the Works, and shall pay all fees and rental for the same. The telephone connection shall
remain on site until completion of the works.
D | SANITATION
The Contractor shall make arrangements for the necessary toilet facilities for their staff and
workmen to the requirements and satisfaction of the Health authorities and maintain the same
in a thoroughly clean and sanitary condition and pay all conservancy fees during the period of
the Works and remove when no longer required.
E | PLANT, TOOLS AND SCAFFOLDING
The Contractor shall provide all necessary hoists, tackle, plant, vehicles, tools and appliances
of on every description for the due and satisfactory completion of the Works and shall remove
same completion.
The Contractor shall provide, erect and maintain all temporary scaffolding, sufficiently strong
and efficient for the due performance of the Works, including Sub-contract Works, provide
special scaffolding as and when required during the Works and remove on completion and
make good.
Such scaffolding shall be constructed of tubular steel or timber of sufficient scantlings and be
provided with planked footways and guard-rails to approval.
All such plant, tools and scaffolding shall comply with all regulations whether general or local, in
force throughout the period of the Contract and shall be altered or adapted during the Contract
as may be necessary to comply with any amendments in or additions to such regulations.
Scaffolding is not measured hereinafter, and the Contractor must allow here or in his rates for
the above.
[5 empty] | Carried To Collection |  |  | US$
A | EXISTING AND ADJACENT PROPERTY
The Contractor must take all steps necessary to safeguard existing and adjacent property,
make good at their own expense any damage to persons or property caused thereon, and
hold the Employer indemnified against any such claim arising.
The Contractor will be held fully responsible for the safety of the existing and adjacent buildings
and for any damage caused in consequence of these Works. They must reinstate all damages
at his own expense and indemnify the Employer against any loss.
The Contractor must take such steps and exercise such care and diligence as to minimize
nuisance from dust, noise or any other cause to the occupiers of the existing and adjacent
property.
B | HOARDING
The Contractor shall enclose the site areas under which work is carried out, with
1.80 meter high barbed wire fence comprising treated blue gum poles at centres not
exceeding 3.0meters and 6No barbed wire strands at equal spacing
The contractors attention is drawn to the fact that some areas of the site are
already built up and shall be in use during the currency of this project. As such
the contractor must allow for keeping his/her employees from interfering with
such other users and preventing and minimizing any nuisance arising from dust,
noise or by way of trespass.
Allow for Provisional length of 100 meters @ (tenderer to insert rate and extend)
B | WATCHING AND LIGHTING
The Contractor shall provide at their risk and cost all watching and lighting as necessary to
safeguard the Works, plant and materials against damage and theft.
C | SIGNBOARD
The Signboard and lettering on same for the display of the General and Sub-Contractors'
names shall be of an approved size with the Employer's name painted thereon. The Architect's
Quantity Surveyor's and other Consultants' names shall be printed in 50 mm letters all to the
Architect's approved design. No other signboard or advertising will be permitted without prior
permission from the Architect.
[5 empty] | Carried To Collection |  |  | US$
A | PRIME COST RATES
Where description of items include a P.C. rate per unit this rate is to cover the net supply
cost of the unit only. The Contractor's price must include for the cost of the unit at the rate
stated, plus waste, taking delivery, storage, fixing in position, profit and overheads.
The actual net cost per unit will be adjusted within the Final Account against the P.C. rate
stated.
PROTECTION AND CLEANING
B | PROTECTION
The Contractor shall cover up and protect from damage, including damage from inclement
weather, all finished work and unfixed materials, including that of Sub-Contractors, etc., to the
satisfaction of the Architect until the completion of the Contract.
C | CLEANING
The Contractor shall, upon completion of the Works, at their own expense, remove and clear
away all surplus excavated materials, plant, rubbish and unused materials and shall leave the
whole of the Site and Works in a clean and tidy state to the satisfaction of the Architect,
including clearing away and making good all traces of temporary access roads, offices, sheds,
camps, etc. Particular care shall be taken to leave clean all floors and windows and to remove
all paint and cement stains. They shall also, at the discretion of the Architect, remove all
rubbish and dirt as it accumulates. The Contractor is to find their own dump and shall pay
all charges in connection therewith.
[5 empty] | Carried To Collection |  |  | US$
Collection
|  | Brought forward from Page |  |  |  | 1/4
|  | Brought forward from Page |  |  |  | 1/5
|  | Brought forward from Page |  |  |  | 1/6
|  | Brought forward from Page |  |  |  | 1/7
|  | Brought forward from Page |  |  |  | 1/8
|  | Brought forward from Page |  |  |  | 1/9
|  | Brought forward from Page |  |  |  | 1/10
|  | Brought forward from Page |  |  |  | 1/11
| TOTAL FOR SECTION 1: PRELIMINARIES AND GENERAL DESCRIPTIONS CARRIED TO GRAND SUMMARY | [5 empty] | US$

## Elevated water tank
XARXAAR BOREHOLE REHABILITATION
Elevated Water Tank 30m3 (8m high)
Item | Description | Unit | Qty | Unit Costs (USD) | Total Costs (USD)
1 | Foundation
1.11 | Excavation: General excavation works for the column's foundations, depth up to 1500mm in all type of soil | m3 | 39.89 |  | 0
1.12 | Lean concrete (2000 x 2000mm, thickness 50mm): lean concrete, mix 1:4:8, ready to receive the the column's foundations | m3 | 1.2 |  | 0
1.13 | Foundations (1400 x 1400mm, thickness 600mm): reinforced concrete class 20 (nominal mix 1:2:4) with Y12 at column bases | m3 | 7.056 |  | 0
2 | Columns and Beams
2.11 | Columns (section: 300mmx 300mm): reinforced concrete mix 1:2:4, with high yield twisted rebar of Y12 and R6 for stirrups @200mm c/c | m3 | 5.83 |  | 0
2.15 | Beam (section 300x450mm), concrete class 20,nominal mix 1:2:4) with Y16 rebar and R8 for beam links | m3 | 9.32 |  | 0
3 | Storage tank (RC slabs and RC walls)
3.11 | Tank slab: (3400 x 6400mm, thickness 1500mm): reinforced concrete class 25 ( nominal mix 1:2:3) complete with water proofing, 12mm dia high yield square twisted bars for tank base slab | m3 | 3.264 |  | 0
3.13 | Water bar: 200mm water bar | Lm | 17 |  | 0
3.14 | Walls: (thickness 12mm and height of 2000mm) reinforced concrete class 25 ( nominal mix 1:2:3) complete with water proofing; 12mm high yield square twisted bars for tank walls | m3 | 3.384 |  | 0
3.16 | Cover slab: (4400 x 4400mm, thickness 150mm): reinforced concrete class 20 (nominal mix 1:2:4), 12mm high yield square twisted bars for tank cover slab | m3 | 1.984 |  | 0
4 | Inspection manhole and fittings
4.11 | Inspection manhole (600mm x 600mm): Reinforced concrete 50mm thick with BS mesh A142, bent up round iron bars handle and 50x50x3mm, using of Y12 HY Square twisted bars at man hole corners | unit | 0.02 |  | 0
4.13 | BS mesh A142 for manhole cover | m2 | 0.4 |  | 0
4.14 | 50x50x3mm L angle plates | lm | 16 |  | 0
4.15 | Fittings: supply and install all fittings for inlet, distribution and trucking outlets and overflow | LS | 1 |  | 0
4.16 | Ladder (500mm width,13m length): Supply and install a metallic ladder, including all anchorage points | unit | 1 |  | 0
Total |  |  |  |  | 0
2

## Generator shed
ITEM NO. | DESCRIPTION |  | UNIT | QUANTITY | RATE (US$) | AMOUNT (US$)
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
ELEMENT NO. 1
SITE PREPARATION
A | Clear site of all trees, bushes and shrubs, grab up roots and
| burn the arisings. |  | SM | 58.5
B | Load, wheel and cart deposit and spread surplus excavated
material where directed on site at a distance not exceeding
| 100 meters |  | LS | 1
| CARRIED TO COLLECTION AT END OF ELEMENT 1 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
ELEMENT NO. 2
SUBSTRUCTURES (PROVISIONAL)
Excavations including maintaining and supporting sides
and keeping free from water, mud and fallen material
A | Excavate trench for foundation not exceeding 1.50 meters
| deep, starting from stripped levels |  | CM | 14.4
Disposal
B | Return, fill and ram selected excavated material around
| foundations |  | CM | 9.6
C | Load, wheel and cart deposit and spread surplus excavated
material where directed on site at a distance not exceeding
| 100 meters |  | CM | 4.8
Hardcore or other approved filling, as described
D | 300mm thick well compacted hardcore filling blinded with
| 25mm thick quarry dust layer to receive surface bed |  | SM | 37
Anti-termite treatment
E | Gladiator or equal and approved chemical anti-termite
treatment, executed complete by an approved specialist
| under a ten-year guarantee, to surfaces of hard-core |  | SM | 37
Damp-proof membrane
F | 1000 gauge polythene or other equal and approved
damp-proof membrane, laid over blinded hardcore
(m.s) with 300mm side and end laps (measured
| nett-allow for laps) |  | SM | 37
Plain concrete class 15 in:
G | 50mm blinding under strip footing |  | SM | 14.4
Reinforced concrete class (20) as described, in:-
H | Strip footing |  | CM | 2.88
I | Litols |  | CM | 0.069
J | 125mm thick surface bed laid in bays including all
| necessary formwork |  | CM | 3
K | Ditto for generator plinths |  | CM | 0.72
Reinforcement, as described:-[PROVISIONAL]
High yield square twisted reinforcement bars to B.S 4461
A | FOOTING
| 8mm bars |  | Kg | 44.424
| 10mm bars |  | Kg | 26.544
B | LINTOLS
| 8mm bars |  | Kg | 3.702
| 10mm bars |  | Kg | 2.212
Mesh fabric reinforcement to B.S 4483 and setting in
concrete with 300mm side and end laps
(measured nett-allow for laps).
C | Fabric ref. A142 weighing 2.22kg/ sq.metre, in surface
| bed |  | SM | 32
D | Ditto for generator plinth |  | SM | 4.8
E | Ditto for ramp |  | SM | 7
Sawn formwork as described to:-
F | To edge of steps and slabs over 75mm but not exceeding
| 150mm high |  | LM | 24
G | Sides and soffits of lintols |  | LM | 2
H | Sides and generator plinth |  | LM | 12.8
| CARRIED TO COLLECTION AT END OF ELEMENT 2 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
ELEMENT NO. 3
WALLING
SUBSTRUCTURE WALLING
Approved compacted rubble stone fill bedded and jointed in
cement sand mortar (1:4)
A | 400mm thick rubble stone foundation walling |  | m3 | 7.68
SUPERSTRUCTURE WALLING
200x400mm hollow block walling bedded and jointed in
cement and sand (1:4) mortar, reinforcement with and
including 25mm wide x 20 gauge hoop iron at every
alternate course as described in:
B | 200mm thick walling Super-structure walling |  | SM | 27
C | Ditto for dwarf wall |  | SM | 10.4
Damp-proof courses, as described, to walls
D | 200mm wide |  | LM | 37.4
E | 100mm dia. Galvanized Circular Hollow Section (CHS)poles |  | No. | 4
F | Heavy duty fabric mesh |  | SM | 26
G | 150x50mm timber framework |  | LM | 48
| CARRIED TO COLLECTION AT END OF ELEMENT 3 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
ELEMENT NO. 4
ROOF CONSTRUCTION AND FINISHES
The following in sawn cellcured timber roof trusses with nailed
connections including hoisting and fixing in position
not exceeding 5.0 meters above ground floor level
A | 100x50mm rafters |  | LM | 60
B | 100x50mm strut or tie |  | LM | 30
C | 100x50mm tie beam |  | LM | 35
D | 100x50mm wall plate fixed with and including 200mm
long 12mm diameter rag bolts cast into beam at 1500mm
| centres |  | LM | 24
Roof sheets as IT4 profile gauge 28 pre-painted galvanised
E | Roof sheets as IT4 profile gauge 28 pre-painted galvanised
roofing sheets laid with 95 mm side and 200 mm end laps
| hook bolts, PVC washer and tropicalized slip cup |  | SM | 38
| CARRIED TO COLLECTION AT END OF ELEMENT 4 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
ELEMENT NO. 5
FINISHES
15 mm cement and sand (1:3) render, finished with
woodfloat to:-
A | Concrete or masonry surfaces internally and externally |  | SM | 37.4
12mm (minimum) two coat lime plaster as described to
B | Concrete or masonry surfaces internally |  | SM | 37.4
Floor Finishes
Cement and sand (1:3) screeds, backings, beds etc
C | 40mm bed finished floor screed |  | SM | 32
Painting and decorating
Prepare and apply three coats first quality emulsion
paint on:-
D | Plastered walls externally |  | SM | 37.4
Prepare and apply three coats first quality silk vinyl
emulsion paint on:-
E | Plastered surfaces internally |  | SM | 37.4
| CARRIED TO COLLECTION AT END OF ELEMENT 5 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
ELEMENT NO. 6
DOORS
Purpose built steel door complete with heavy gauge
mesh on 2" diameter galvanized iron framework.
framework including cutting handling, hoisting fixing in position
at all heights with all necessary ironmongery and
applying a priming coat of approved steel primer.
A | Double door overall size 2800x2700mm high |  | No. | 1
double leaf
B | Single door overall size 900x2100mm high
| single leaf |  | No. | 1
Allow for PCC vents
C | 2000X1000mm high |  | LS | 1
| CARRIED TO COLLECTION AT END OF ELEMENT 6 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
ELEMENT NO. 7
ELECTRICAL INSTALLATION AND SERVICES
Lighting Fittings
Supply and install following lighting fixtures with all accessories
as per the specifications and drawings and complete with lamp
fitting and accessories of Engineer or approved make.
A | 1200mm flourescent tube lighting |  | No. | 3
| 150W LED floodlight |  | No. | 1
Switches
B | 5 Amps 3 gang one way switch |  | No | 1
C | 5 Amps 2 gang one way switch |  | No | 1
Socket outlets
Supply and installation of fused shuttered switched socket outlet
to comply with relevant BS standard (Clipsal, Orange, Crabtree/
Tenby/ABB or equivalent). Wiring (including supply of earth wire
and all other material required) of above socket outlet using approved
type 2.5mm² PVC/PVC copper cable and 2.5mm² earth wire drawn
through securely fixed concealed PVC conduit in a ring circuit.
Socket outlet points
D | 13 A twin sockets outlet |  | No | 2
Cables, Cable pathways and Conduits
Supply, install, test and commission 450/750 volts 6491X cables with
all required accessories for proper installation and operation including
conduits, pipes( each cable in separate conduit or pipe), cable lugs,
ties... etc. as shown on drawing, as per the preamble, the specifications
and supervision engineer's requirements.
E | Supply, install and connect complete 1.5 sq. mm colour-coded SC
cables to lighting points drawn in Concealed /surface 20mm HG PVC
conduits, complete with draw boxes, switch boxes and other necessary
| accessories. |  | M | 10
F | Supply and install two compartment floor recessed metallic electrical
floor box with flap cover complete with lifting handle, cable cable flaps,
| as Crabtree Britmac or equal and approved |  | No. | 1
| CARRIED TO COLLECTION AT END OF ELEMENT 7 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 3: GENERATOR SHED
MAIN SUMMARY
| ELEMENT | TITLE |  | PAGE |  | AMOUNT
NO
| 1 | SITE PREPARATION |  | 2/1
| 2 | SUBSTRUCTURES (PROVISIONAL) |  | 2/2
| 3 | WALLING |  | 2/3
| 4 | ROOF CONSTRUCTION AND FINISHES |  | 2/4
| 5 | FINISHES |  | 2/5
| 6 | DOORS |  | 2/6
| 7 | ELECTRICAL INSTALLATION AND SERVICES |  | 2/7
Grand Total
| TOTAL CARRIED TO GRAND SUMMARY |  | US$

## Borehole
ITEM | DESCRIPTION |  |  | UNIT | QNTY | RATE US$ | AMT US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 5: BOREHOLE REHABILITATION
ELEMENT 1: SUPPLIES
1 | Submersible pump, Grundfos, SP8A - 18, with matching cut-off electrodes,
| drop cables control panel, all accessories included ( Stand by Pump) |  |  | each | 1
2 | Procure and install, Pipe, Galvanized iron, 5.8 metres long, 3" (75 mm)
| nominal diameter, rated for 14 Bar pressure in borehole |  |  | No | 33
3 | Pipe, uPVC class D, 5.8 metres long, 90mm nominal diameter, rated for
| 10 Bar pressure |  |  | No | 35
4 | Pipe, Galvanized iron, 5.8 metres long, 1" (50mm)nominal diameter,
| rated for 14 Bar pressure |  |  | No | 20
5 | uPVC pipe class D, 50mm OD, 10 bar, 5.8m length |  |  | No | 42
6 | Allow lumpsum for installation of gantry using 4" CHS and 'I' Beam including
| cutting, joining, welding and fixing in place |  |  | LS | 1
| CARRIED TO COLLECTION AT END OF ELEMENT 1 |  |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 5: BOREHOLE REHABILITATION
MAIN SUMMARY
| ELEMENT | TITLE |  | PAGE |  |  | Amount
NO
| 1 | ELEMENT 1: SUPPLIES |  | 2/1
Grand Total
| TOTAL CARRIED TO GRAND SUMMARY |  | US$

## Piping
ITEM | DESCRIPTION |  |  | UNIT | QUANTITY | RATE (USD) | AMOUNT (USD)
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 6 : PIPELINE
ELEMENT NO. 1: EXCAVATION
Excavation including maintaining and supporting sides and keeping
free from water, mud and fallen materials by bailing, pumping or otherwise
A | Prepare site by stripping top 200 mm of soil to remove all debris including
| sand (if any) from site and carting away spoil |  |  | m2 | 150
B | Excavate for foundation strip commencing at stripped levels depth not
| exceeding 1.50m deep |  |  | m3 | 120
D | Remove surplus excavated material from site |  |  | m3 | 36
| CARRIED TO COLLECTION AT END OF ELEMENT 1 |  |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 6 : PIPELINE
ELEMENT NO. 2: PIPELINE
| Supply and install high pressure UPVC pipe 3" diameter x 6m length, the price includes |  |  | No. | 50
all type of bends, elbows, tees, and laying metallic plastic tracer tape … etc,
to connect all as noted above, described in the Specifications and as shown
on the detailed drawings and as directed by the Engineer.
| Supply and install all required fittings (Tees, elbows, Flanges, reducers/extruders, |  |  | LS | 1
couplings, spigots, required steel pipes, gaskets, SS bolts, … etc, to connect
the proposed UPVC pipe according to Detail. The price should exclude the gate
valve and its connection fittings (to be in a separate item).
| Allow for 3" brass gate valves |  |  | No. | 6
| CARRIED TO COLLECTION AT END OF ELEMENT 1 |  |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 6 : PIPELINE
ELEMENT NO. 3: BACKFILLING
E | Backfill around foundations |  |  | m3 | 84
| CARRIED TO COLLECTION AT END OF ELEMENT 1 |  |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 6 : PIPELINE
MAIN SUMMARY
| No. | ELEMENT | TITLE |  | PAGE |  | Amount
| 1 | ELEMENT NO. 1: EXCAVATION
| 2 | ELEMENT NO. 2: PIPELINE
| 3 | ELEMENT NO. 3: BACKFILLING
| Grand Total |  |  | US$
| TOTAL FOR SECTION 4: CARRIED TO GRAND SUMMARY |  |  | US$

## Caretakers room
ITEM NO. | DESCRIPTION |  | UNIT | QUANTITY | RATE (US$) | AMOUNT (US$)
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
ELEMENT NO. 1: SITE PREPARATION
A | Clear site of all trees, bushes and shrubs, grab up roots and
| burn the arisings. |  | SM | 12
B | Load, wheel and cart deposit and spread surplus excavated
material where directed on site at a distance not exceeding
| 100 meters |  | LS | 1
| CARRIED TO COLLECTION AT END OF ELEMENT 1 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
ELEMENT NO. 2: SUBSTRUCTURES (PROVISIONAL)
Excavations including maintaining and supporting sides
and keeping free from water, mud and fallen material
A | Topsoil excavation average 200mm deep |  | CM | 2.4
B | Excavate trench for foundation not exceeding 1.50 meters
| deep, starting from stripped levels |  | CM | 7.2
Disposal
C | Return, fill and ram selected excavated material around
| foundations |  | CM | 4.8
D | Load, wheel and cart deposit and spread surplus excavated
material where directed on site at a distance not exceeding
| 100 meters |  | CM | 2.4
Hardcore or other approved filling, as described
E | 300mm thick well compacted hardcore filling blinded with
| 25mm thick quarry dust layer to receive surface bed |  | CM | 4.35
Anti-termite treatment
F | Gladiator or equal and approved chemical anti-termite
treatment, executed complete by an approved specialist
| under a ten-year guarantee, to surfaces of hard-core |  | SM | 4.35
Damp-proof membrane
G | 1000 gauge polythene or other equal and approved
damp-proof membrane, laid over blinded hardcore
(m.s) with 300mm side and end laps (measured
| nett-allow for laps) |  | SM | 4.35
Plain concrete class 15 in:
H | 50mm blinding under strip footing |  | SM | 7.5
Reinforced concrete class (20) as described, in:-
I | Ground beam |  | CM | 1.44
J | Litols |  | CM | 1.08
K | 200mm thick surface bed laid in bays including all
| necessary formwork |  | CM | 2.5
Reinforcement, as described:-[PROVISIONAL]
High yield square twisted reinforcement bars to B.S 4461
A | GROUND BEAM
| 10mm bars |  | Kg | 29.616
| 8mm bars |  | Kg | 13.272
B | LINTOLS
| 10mm bars |  | Kg | 2.9616
| 8mm bars |  | Kg | 1.3272
Mesh fabric reinforcement to B.S 4483 and setting in
concrete with 300mm side and end laps
(measured nett-allow for laps).
C | Fabric ref. A142 weighing 2.22kg/ sq.metre, in surface
| bed |  | SM | 4.35
Sawn formwork as described to:-
D | To edge of slab |  | SM | 2.4
E | To edge of steps and slabs over 75mm but not exceeding
| 150mm high |  | SM | 0.4
F | Sides and soffits of lintols |  | SM | 0.6
| CARRIED TO COLLECTION AT END OF ELEMENT 2 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
ELEMENT NO. 3: WALLING
SUBSTRUCTURE WALLING
Approved compacted rubble stone fill bedded and jointed in
cement sand mortar (1:4)
A | 400mm thick rubble stone foundation walling |  | m3 | 3.84
SUPERSTRUCTURE WALLING
200x400mm hollow block walling bedded and jointed in
cement and sand (1:4) mortar, reinforcement with and
including 25mm wide x 20 gauge hoop iron at every
alternate course as described in:
B | 200mm thick walling Super-structure walling |  | SM | 32.4
Damp-proof courses, as described, to walls
C | 200mm wide |  | LM | 12
| CARRIED TO COLLECTION AT END OF ELEMENT 3 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
ELEMENT NO. 4: ROOF CONSTRUCTION AND FINISHES
The following in sawn cellcured timber roof trusses with nailed
connections including hoisting and fixing in position
not exceeding 5.0 meters above ground floor level
A | 100x50mm rafters |  | LM | 20
B | 100x50mm collar |  | LM | 6
C | 100x50mm tie beam |  | LM | 16
D | 100x50mm wall plate fixed with and including 200mm
long 12mm diameter rag bolts cast into beam at 1500mm
| centres |  | LM | 12
Roof sheets as IT4 profile gauge 28 pre-painted galvanised
E | Roof sheets as IT4 profile gauge 28 pre-painted galvanised
roofing sheets laid with 95 mm side and 200 mm end laps
| hook bolts, PVC washer and tropicalized slip cup |  | SM | 26
F | 25mm soft board ceiling |  | SM | 10
| CARRIED TO COLLECTION AT END OF ELEMENT 4 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
ELEMENT NO. 5: FINISHES
15 mm cement and sand (1:3) render, finished with
woodfloat to:-
A | Concrete or masonry surfaces internally and externally |  | SM | 32.4
12mm (minimum) two coat lime plaster as described to
B | Concrete or masonry surfaces internally |  | SM | 32.4
Floor Finishes
Cement and sand (1:3) screeds, backings, beds etc
C | 40mm bed finished floor screed |  | SM | 4.35
Painting and decorating
Prepare and apply three coats first quality emulsion
paint on:-
D | Plastered walls externally |  | SM | 32.4
Prepare and apply three coats first quality silk vinyl
emulsion paint on:-
E | Plastered surfaces internally |  | SM | 32.4
F | Soffits of ceiling |  | SM | 10
| CARRIED TO COLLECTION AT END OF ELEMENT 5 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
ELEMENT NO. 6: DOORS
Purpose built steel door complete with heavy gauge
mesh on 2" diameter galvanized iron framework.
framework including cutting handling, hoisting fixing in position
at all heights with all necessary ironmongery and
applying a priming coat of approved steel primer.
A | Single door overall size 900x2100mm high
| single leaf |  | No. | 1
Allow for PCC vents
B | 1000X300mm high |  | LS | 3
| CARRIED TO COLLECTION AT END OF ELEMENT 6 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
ELEMENT NO. 7: ELECTRICAL INSTALLATION AND SERVICES
Lighting Fittings
Supply and install following lighting fixtures with all accessories
as per the specifications and drawings and complete with lamp
fitting and accessories of Engineer or approved make.
A | 1200mm flourescent tube lighting |  | No. | 2
Switches
B | 5 Amps 2 gang one way switch |  | No | 1
Socket outlets
Supply and installation of fused shuttered switched socket outlet
to comply with relevant BS standard (Clipsal, Orange, Crabtree/
Tenby/ABB or equivalent). Wiring (including supply of earth wire
and all other material required) of above socket outlet using approved
type 2.5mm² PVC/PVC copper cable and 2.5mm² earth wire drawn
through securely fixed concealed PVC conduit in a ring circuit.
Socket outlet points
D | 13 A twin sockets outlet |  | No | 1
Cables, Cable pathways and Conduits
Supply, install, test and commission 450/750 volts 6491X cables with
all required accessories for proper installation and operation including
conduits, pipes( each cable in separate conduit or pipe), cable lugs,
ties... etc. as shown on drawing, as per the preamble, the specifications
and supervision engineer's requirements.
E | Supply, install and connect complete 1.5 sq. mm colour-coded SC
cables to lighting points drawn in Concealed /surface 20mm HG PVC
conduits, complete with draw boxes, switch boxes and other necessary
| accessories. |  | M | 10
F | Supply and install two compartment floor recessed metallic electrical
floor box with flap cover complete with lifting handle, cable cable flaps,
| as Crabtree Britmac or equal and approved |  | No. | 1
| CARRIED TO COLLECTION AT END OF ELEMENT 7 |  | US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 7: CARETAKERS ROOM
MAIN SUMMARY
| Ref. | TITLE |  | PAGE
| 1 | ELEMENT NO. 1: SITE PREPARATION |  | 2/1
| 2 | ELEMENT NO. 2: SUBSTRUCTURES (PROVISIONAL) |  | 2/2
| 3 | ELEMENT NO. 3: WALLING |  | 2/3
| 4 | ELEMENT NO. 4: ROOF CONSTRUCTION AND FINISHES |  | 2/4
| 5 | ELEMENT NO. 5: FINISHES |  | 2/5
| 6 | ELEMENT NO. 6: DOORS |  | 2/6
| 7 | ELEMENT NO. 7: ELECTRICAL INSTALLATION AND SERVICES |  | 2/7
Grand Total
| TOTAL CARRIED TO GRAND SUMMARY |  | US$

## Water Kiosk-
PROPOSED XARXAAR BOREHOLE REHABILITATION
Cosntruction of Water Kiosk
| DESCRIPTION | UNIT | QTTY | RATE | AMOUNT
1 | Site clearance: leveling and clear unnecessary materials | M2 | 5.9496 |  | 0
2 | Excavation foundation trench and level (2.22m x 2.68 x0.3 | M3 | 1.7849 |  | 0
3 | Mass concrete of 50mm thick blinding layer (1:2:4 mix) under the foundation wall 2.22m x 2.68 x0.05) | M3 | 0.29748 |  | 0
4 | 250mm hardcore filling and well compacting for slab area(2.22mx2.68m) | M3 | 1.4874 |  | 0
5 | RC concrete (1:2:4 mix ) in conc. floor slab 10 cm thick(2.22mx2.68mx0.1m) | M3 | 0.59496 |  | 0
6 | 20cm thick masonry walling in cement & sand mortar 1;3 mix () | M3 | 1.0586 |  | 0
7 | Cast 20cm Mass concrete 1:3:6 mix design of the area (1.58x0.2x0.1m) | M3 | 0.0316 |  | 0
8 | External & internal plastering ,12 mm thick, cement and sand mix 1:4, with wood float finish. | M2 | 7 |  | 0
9 | Apply two coats of white wash | M2 | 7 |  | 0
10 | 30 mm thick 1:3 cement/sand floor screed | M3 | 0.3 |  | 0
11 | GI pipes for water Kiosk 1'' | Pcs | 4 |  | 0
| Fittings on the kiosk |  |  |  | 0
12 | GI Reducer 2" -1" | Pcs | 2 |  | 0
13 | 900 GI Elbow 1" | Pcs | 2 |  | 0
14 | 1" GI Double Tee | Pcs | 2 |  | 0
15 | 1" GI Single Tee | Pcs | 1 |  | 0
16 | Reducer socket 1"-3/4" | Pcs | 6 |  | 0
17 | Nipple GI | Pcs | 6 |  | 0
18 | Branch pipes, 3/4", galvanised (long pipe 300mm threaded on both sides ) | Pcs | 6 |  | 0
19 | 3/4" taps | Pcs | 6 |  | 0
20 | Visibility bill board (1.2mx1m) with a 11/2 GI pipe legs and length of 3m the GI pipe should fix concrete at the bottom. | LS | 1 |  | 0
21 | Pit excavation commencing at reduced levels depth not exceeding 1.5m deep. | LS | 1 |  | 0
| Sub-total for One Kiosk |  |  |  | 0
| No. of water kiosks |  | 2 |  | 0
| SUB TOTAL CARRIED TO MAIN SUMMARY |  |  |  | 0

## Fence
ITEM | DESCRIPTION |  | UNIT | QNTY | RATE US$ | AMT US$
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 9: FENCE AND GATE
ELEMENT No. 1: GATE
The contractor will provide all material and construct a steel
gate maesuring approximately 4500x2100m.
Given the location and site conditions, the contractor is
advised to make a physical assesment of the site before
tendering.
A | Excavate for column pads, depth not exceeding
1.5m and of 1.5 x 1.5 mm width commencing at the original
| ground level, and cart away to spoil as directed |  | CM | 6.75
Reinforced Concrete using 3/4 + 1/2" mix machine
crushed Ballast in:
B | Vibrated reinforced concrete (class 25) column base, 350mm deep |  | CM | 0.7875
C | Ditto in columns 600x600mm thick, average height of 2.7 m
| with 1.5 m being the foundation column |  | CM | 1.944
D | Assorted high tensile twisted steel reinforcement bars to B.S 4446. |  | KG | 200
E | Sawn formwork to vertical sides of the columns |  | SM | 10
F | 15mm thick cement/Sand plaster to vertical sides of the columns |  | SM | 10
G | 350x350x25mm thick P.C.C coping stone |  | No | 2
Main and pedestrian gates
H | Supply and fix double leaf steel gate size 3000x 2100mm high
CHS poleswith small pedestrian door made from 2"x 3mm thick
welded on one side of the frame. Frame as follows: 75 x 3mm
thick RHS external members and 25mm SHS 3mm thick secondary
members, fixed onto the concrete columns using heavy duty steel
pin hinges; with all fastening accessories including all cutting
welding, grinding and priming with one coat of grey oxide before
fixing. The gate should also have peep holes of not more that
25mm dia with a slilding door. It should also have 2 locking
| mechanisms, top and bottom. |  | NO | 2
Sub-Total for main and pestrian gate
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 9: FENCE AND GATE
ELEMENT No. 2 : FENCE
The contractor is reminded to include in his pricing,
the cost of supply, cutting, waste and erection and all other
necessary fittings including welding lugs or fishtailing onto
the 50x50x6mm angle bars. Angle bars and the necessary
fixing and anchorage to be treated as described in the
specifications.
Fence construction should be according to BS 1722-Part 10
A | Clear the perimeter of the fencing area of all bushes scrubs and obstructions |  | SM | 96
B | Excavate 300x300x500 deep holes to receive mass concrete (1:3:6)
| bases as shown in the drawings. |  | CM | 2.4
C | Supply 50x5mm CHS welded to form Y-shaped posts with ends closed as
shown in the drawings, bottom end fixed with 100x100mmx3mm plate
and bedded in mass concrete.The post to be 2500mm high from ground
| level to the Y-joint. Allow for drlling 7No holes as shown. |  | NO | 53.3333
D | Extra Over 50x5mm posts for bracing on either side every fourth
| intermediate post and all corner posts. |  | NO | 13.3333
Mass Concrete Mix 1:3:6/20mm using 3/4 Local Ballast in:
E | Supply all materials and cast 0.3m diameter x 0.6m depth mass concrete
class Q (1:3:6) to concrete the 50mm dia. CHS poles while ensuring they
remain plumb 600mm deep below the ground level and 2500mm (2.5m)
| above ground level. |  | CM | 2.4
F | Supply and weld a 12mm high tensile steel rod along the bases of the posts
for anchoring the chainlink to the ground along the whole length of the fence.
| Allow for excavating 200mm deep along the fence to fix the rod. |  | LM | 160
G | Allow for curing of all concrete works |  | Item | 1
H | Supply and fix 3No strands of 12G barbed wire bound onto either sides
| of the Y post using 3mm galvanised wire as shown in the drawings. |  | LM | 960
I | Ditto for posts |  | LM | 1120
J | Supply and and fix 2500mm high HEAVY GUAGE chainlink to posts using 3mm
galvanised wire. Allow for securing the chainlink to a 12mm reinforcement
| bar welded at the base btween the posts. |  | LM | 160
K | Supply and fix razer wire secured on the chainlink, barbed wire and Y posts
| by binding wire and rolled approximately 600mm dia. |  | LM | 160
L | Prepare and apply one under coat of epoxy based primer and two finishing
| epoxy based paints to metal surfaces n.e 250mm in alternate bands of 300mm |  | No. | 66.6667
Total carried to summary
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
SECTION 9: FENCE AND GATE
ELEMENT NO. 3 : MAIN SUMMARY
| ELEMENT No. | TITLE |  | PAGE |  | Amount
| 1 | ELEMENT No. 1: GATE |  | 1/2
| 2 | ELEMENT No. 2 : FENCE |  | 2/2
Total
Total carried to grand summary

## Grand summary
ITEM NO. | DESCRIPTION | PAGE | AMOUNT (US$)
PROPOSED XARXAAR BOREHOLE REHABILITATION
GALKAYO DISTRICT
GRAND SUMMARY
1 | SECTION 1: PRELIMINARIES AND GENERAL DESCRIPTIONS
2 | SECTION 2: ELEVATED WATER TANK |  | 0
3 | SECTION 3: GENERATOR SHED
4 | SECTION 5: BOREHOLE REHABILITATION
5 | SECTION 6 : PIPELINE
6 | SECTION 7: CARETAKERS ROOM
7 | SECTION 8: WATER KIOSK |  | 0
8 | SECTION 9: FENCE AND GATE
| TOTAL AMOUNT CARRIED TO FORM OF TENDER | US$
SIGNED:
(CONTRACTOR) ……………………………………………………………………………………………………………………
Address: ………………………………………………………………………………………………………………………………………
Tel No: ………………………………………………………………………………………………………………………………………
Date: ……………………………………………………………………………………………………………………………………………
SIGNED:
(EMPLOYER ) …………………………………………………………………………………………………………………………
Address: ……………………………………………………………………………………………………………………………………
Tel No: ………………………………………………………………………………………………………………………………………
Date: ………………………………………………………………………………………………………………………………………….